## Risk Register
Asset | Threat | Vulnerability | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Level | Existing Controls | Recommended Controls | Control Mapping (ISO 27001) | Owner | Status
Electronic Medical Records (EMR) | Ransomware | Unpatched systems | 4 | 5 | 20 |  | Basic AV | Implement EDR, patching policy, offline backups | A.5, A.8, A.12 | ICT Officer | Open
Patient Registration System | Data Breach | Weak passwords | 3 | 4 | 12 |  | Password policy | MFA, password vaulting | A.5, A.9 | Systems Admin | In Progress
Network Switches | Unauthorized Access | Default credentials | 5 | 5 | 25 |  | Network segmentation | Credential hardening, monitoring | A.8, A.13 | Network Engineer | Open
Backup Server | Data Loss | No offsite backup | 2 | 5 | 10 |  | Local backup only | Offsite/cloud backup | A.12, A.17 | ICT Manager | Planned