## Sheet1
NC ID | Date Found | Source | Clause / Annex A | Description of Finding | Severity | Root Cause Analysis (RCA) | Correction (Immediate Action) | Corrective Action Plan (Long-term) | Target Date | Status | Closure Date
NC-01 | 2025-01-10 | Stage 1 Audit | 6.1.2 | Risk Acceptance Criteria not formally defined or approved by Top Management. | Major | ISMS methodology was drafted but formal approval phase was skipped in the project plan. | Risk criteria were drafted and presented to the Board. | Update the ISMS Governance Manual to require annual Board approval of risk criteria. | 2025-01-20 | Closed | 2025-01-22
MN-01 | 2025-01-10 | Stage 1 Audit | A.5.2 | IS Policy exists but lacks evidence of communication to all department heads. | Minor | Lack of a centralized tracking mechanism for policy acknowledgement. | Distributed policy via email and collected manual signatures from 10/10 Dept Heads. | Implement a "Policy Portal" on the hospital intranet for automated digital sign-offs. | 2025-02-15 | Closed | 2025-02-10
M-01 | 2025-02-28 | Stage 2 Audit | A.8.1 (2022) | Sample check of 5 laptops showed 2 lacked full-disk encryption (BitLocker disabled). | Major | Group Policy (GPO) failed to sync on devices that hadn't connected to the hospital VPN for 30+ days. | Immediately recalled the two devices and manually applied encryption. | Update GPO settings to enforce encryption offline and implement a monthly MDM compliance report. | 2025-03-30 | Open | -
m-01 | 2025-02-28 | Stage 2 Audit | 8.2 | The Risk Treatment Plan (RTP) references an outdated version (v1.1) of the Access Control Policy. | Minor | Manual documentation update error; document control process was not followed for the RTP. | Updated the RTP reference to the current version (v2.0) immediately. | Provide refresher training to the ISMS Team on Document Control and versioning procedures. | 2025-03-15 | In Progress | -
OFI-01 | 2025-02-28 | Stage 2 Audit | 7.3 | Awareness training is general; could benefit from clinical-specific PHI handling scenarios. | OFI | Training was generic to suit all staff, rather than tailored to clinical workflows. | N/A (Improvement Suggestion) | Revise Q3 Security Awareness training to include "Nurse-specific" data handling scenarios. | 2025-06-01 | Open | -