## Sheet1
ID | Domain | Requirement / Control | Hospital-Specific Action Item | Priority | Status | Owner | Evidence Document
4.3 | Context | ISMS Scope | Define boundaries (e.g., Clinical Networks, EHR, Billing). | High | 🟢 | CISO | isms-scope-statement.docx
5.2 | Leadership | ISMS Policy | Approve the overarching security mandate for the hospital. | High | 🟢 | CEO | policies/IS-Policy.pdf
6.1 | Planning | Risk Assessment | Conduct risk assessment for patient data (PHI) workflows. | Critical | 🟡 | IT Mgr | hospital-risk-register.xlsx
6.1.3 | Planning | SoA | Finalize the Statement of Applicability for medical controls. | High | 🔴 | CISO | Statement-of-Applicability.xlsx
7.3 | Support | Awareness | Conduct HIPAA/ISO training for clinical and nursing staff. | High | 🟡 | HR/CISO | Training Attendance Logs
7.5 | Support | Documentation | Establish version control for clinical security procedures. | Med | 🟢 | ISMS Mgr | ISMS-Doc-Control-Proc.pdf
8.1 | Operations | Change Mgmt | Implement security checks for EHR and PACS updates. | High | 🔴 | IT Ops | Change Request Logs
A.5.15 | Annex A | Access Control | Role-based access (RBAC) for doctors, nurses, and admin. | Critical | 🟡 | IT Mgr | Access Control Matrix
A.5.17 | Annex A | Authentication | Enforce Multi-Factor Authentication (MFA) for remote access. | High | 🟡 | IT Ops | System Config Screenshots
A.5.30 | Annex A | ICT Continuity | Disaster Recovery testing for the Electronic Health Record. | Critical | 🟡 | BCP Lead | DR Test Report
A.7.12 | Annex A | Physical Sec. | Secure server rooms and nursing stations (clean desk). | Med | 🟢 | Facilities | Physical Access Logs
A.8.1 | Annex A | Endpoint Sec. | Encrypt all mobile nursing tablets and doctor laptops. | High | 🔴 | IT Ops | MDM Compliance Report
A.8.10 | Annex A | Data Deletion | Secure shredding of physical lab results and X-rays. | Med | 🟢 | Facilities | Disposal Certificates
A.8.25 | Annex A | Network Sec. | Segregate Medical IoT (MRI, monitors) from guest Wi-Fi. | High | 🔴 | Network | Network Diagram
9.2 | Evaluation | Internal Audit | Perform an internal "Dry Run" audit before Stage 2. | High | 🔴 | Auditor | internal-audit-report.docx
9.3 | Evaluation | Mgmt Review | Present ISMS progress to the Hospital Medical Board. | Med | 🔴 | CEO | Mgmt Review Minutes
10.2 | Improve | Corrective Action | Log and resolve findings from the Stage 1 Audit. | High | 🟡 | ISMS Mgr | nc-log.xlsx